VERTICAL STUDIO

Master Plan — 4 Parallel AI-Generated Mini-Series

TikTok · YouTube Shorts · Instagram Reels

Owner: Viktar Dzenisevich

Plan version: v1.0 · 12 May 2026

# 1. Executive Summary

This document is the operating plan for launching a fully automated vertical-video studio that produces 4 parallel mini-series for TikTok, YouTube Shorts, and Instagram Reels. The studio is designed to run unattended day-to-day, with the owner approving only two gates: (1) production budget per week, (2) paid-marketing spend per campaign.

Format. 30–60 second vertical episodes (9:16). Each series ships 2 episodes per week (8 episodes/week across the studio). After Day 30 we double-down on the 1–2 best-performing series and either kill or pivot the weakest ones.

Production stack. Sora 2 for hero shots (you already have an account), Flux/SDXL or Midjourney for thumbnails and inserts, ElevenLabs Flash v2.5 for voiceover, FFmpeg/CapCut for assembly, n8n for orchestration, and the official TikTok/YouTube/Meta APIs for posting. Total operating cost target: under $150/month at 32 episodes/month.

Why 4 series in parallel. A single series rarely wins. Running 4 distinct concepts in parallel for 30 days lets us treat the launch as an A/B/C/D test of formats, hooks, and audiences, then concentrate spend on the winner.

## 1.1 The 4 series at a glance

| # | Series | Genre | Hook | Why it works on Sora |
| --- | --- | --- | --- | --- |
| S1 | THE LAST SIGNAL | Sci-fi / horror | Astronaut alone on a dying station starts receiving messages from her own future | Dark interiors + atmospheric VFX — Sora's strong zone; no clear faces needed |
| S2 | ECHOES | Mystery / time-loop | A woman wakes up one day earlier every morning — she has 7 days to stop her own murder | Mostly cinematic POV shots; minimal dialogue; reusable apartment set |
| S3 | 2099 | Cyberpunk anthology | Day-in-the-life of a different stranger in a neon dystopia each episode | Anthology = no character consistency required; ideal for AI video |
| S4 | UNSENT | Emotional drama anthology | Each episode is one message that was typed but never sent — and what would have changed | Text-on-screen heavy → low video minutes → cheapest series to produce |

Each series is treated as its own brand: own handle on each platform, own visual identity, own audio signature. The studio runs them in parallel from one back-office.

# 2. Objectives & KPIs

## 2.1 90-day objectives

- Ship 8 episodes per week across 4 series (32/month, ~96 in 90 days).

- Hit 100k cumulative views by Day 30, 1M by Day 60, 5M by Day 90.

- Cross at least one platform monetization threshold: TikTok Creator Rewards (10k followers + 100k qualified views in 30 days) OR YouTube Shorts revenue (1k subs + 10M Shorts views in 90d) OR Instagram Bonuses (invite-only).

- Identify the winning series by Day 30 and concentrate 60% of production capacity on it.

## 2.2 KPI dashboard (tracked daily)

| KPI | Definition | Day-7 target | Day-30 target | Day-90 target |
| --- | --- | --- | --- | --- |
| Episodes shipped | Posted across all 3 platforms | 12 | 32 | 96 |
| Avg watch-through | Avg % of video watched | 45% | 55% | 65% |
| Hook retention | % still watching at 3s | 65% | 75% | 82% |
| Views per ep (median) | Median across all eps | 500 | 2,500 | 15,000 |
| Follower velocity | New followers per 1k views | 8 | 15 | 25 |
| Cost per 1k views | Production $ ÷ views × 1000 | $8 | $2 | $0.50 |
| Production cost / ep | Token + API cost | $5 | $3 | $2 |

# 3. Operating Model

## 3.1 Two approval gates only

You approve only the following. Everything else runs on autopilot.

| Gate | Frequency | What you see | What you approve | Default if no answer in 24h |
| --- | --- | --- | --- | --- |
| Production budget | Weekly (Mondays) | Episode plan + token + API cost forecast for the next 7 days | Total $ for the week | Auto-approve up to weekly cap of $40 |
| Marketing budget | Per campaign | Boost plan (creator, hook variant, target audience, $ amount, expected CPM) | Each paid push | No spend — organic only |

## 3.2 Roles (all but Owner are Claude/automation)

- Owner (you). Approves the two gates above, makes the kill/scale call on Day 30 and Day 60.

- Trend Scout (auto). Daily scrape of trending sounds, hooks, and topics from TikTok Creative Center, YouTube Trends, Reels search, plus 3 niche subreddits. Output: top-10 hooks of the day per series.

- Showrunner (auto). Writes the next episode for each active series given last week's analytics and today's trend feed. Output: script + Sora prompts + voiceover script + captions.

- Producer (auto). Generates Sora clips, voiceover, picks music, assembles in FFmpeg, renders 9:16 at 1080×1920, ≤60 s.

- Publisher (auto). Schedules posts at peak slots per platform per series, handles the platform-specific copy and hashtags.

- Analyst (auto). Pulls metrics each morning, updates the KPI dashboard, flags wins and kill-candidates.

- Marketer (auto). Drafts boost plans, manages comment seeding, plans cross-promotions and creator collabs.

## 3.3 Weekly cadence

| Day | Owner action | Studio action (auto) |
| --- | --- | --- |
| Monday | Approve weekly production budget (5 min) | Trend scout report + week plan delivered 9:00; production starts |
| Tuesday | — | Episodes 1 & 2 (S1, S2) render and post at peak slots |
| Wednesday | Optional: approve any paid boosts | Episodes 3 & 4 (S3, S4) post; mid-week analytics digest at 18:00 |
| Thursday | — | Episodes 5 & 6 post; trend re-scrape |
| Friday | Approve weekend boosts (5 min) | Episodes 7 & 8 post; weekend retention campaign |
| Saturday | — | Posting + comment seeding only |
| Sunday | Read weekly report (10 min) | Full weekly KPI report 20:00; backlog for next week prepared |

# 4. Technology Stack

| Layer | Tool | Cost model | Monthly cost @ 32 eps | Notes |
| --- | --- | --- | --- | --- |
| Trend scrape | TikTok Creative Center (free) + YouTube Data API (free quota) + Reddit API | Free | $0 | Hits free quota safely |
| Writing | Claude Sonnet 4.6 via API or Claude.ai | ~$0.015/ep | $0.50 | Use Haiku for low-stakes copy |
| Hero video | Sora 2 (your existing account) | Subscription | Included | 6 clips × 5s per episode |
| Insert images | Flux Schnell (Replicate) or Midjourney | $0.003/img | $3 | ~30 images/mo |
| Voiceover | ElevenLabs Flash v2.5 | $0.05/1k chars | $5 | ~1500 chars/ep × 32 |
| Music | Epidemic Sound or YouTube Audio Library | $15/mo or free | $15 | One sub covers all 4 series |
| Assembly | FFmpeg (free) + CapCut (free) | Free | $0 | Headless render on your machine |
| Orchestration | n8n self-hosted (free) or n8n.cloud | Free or $20 | $0–$20 | One n8n covers all 4 series |
| Posting | TikTok Content Posting API + YouTube Data API + Instagram Graph API | Free quotas | $0 | Apply for TikTok Content Posting API early — 1–3 week approval |
| Hosting | DigitalOcean droplet ($6) for n8n + cron | $6/mo | $6 | Skip if running n8n on a local machine |
|  |  | TOTAL | $30–$50 |  |

Token budget is engineered to stay near $5/month even at full output. The expensive units are Sora (already covered by your subscription) and ElevenLabs voiceover. Text generation is the cheapest line item by an order of magnitude.

## 4.1 Token-cost minimization tactics

- Use Claude Haiku 4.5 for trend scraping summaries, comment replies, and hashtag generation. Use Sonnet only for original scripts.

- Cache Series Bible, character voices, and previous episode synopses as a system prompt prefix — paid-cache hits are 90% cheaper.

- Reuse Sora clips across episodes whenever the environment matches. Generate 'B-roll banks' once per series (10 establishing shots) and recombine.

- Anthology series (S3 2099, S4 UNSENT) do not require character consistency — Sora is dramatically cheaper for these than for serialized shows.

- Voiceover: pre-compute the entire week's audio in one ElevenLabs batch — caches voice settings, reduces per-call overhead.

- Skip on-screen English text generation through video models — overlay text in FFmpeg using a CSV → drawtext filter. Zero token cost.

# 5. 30-Day Launch Plan

## Week 1 — Foundation (this week)

- Day 1 (today). Approve Master Plan. Owner creates 12 platform accounts: 4 series × 3 platforms. Owner sets a separate email + phone-verified handle per series.

- Day 2. Studio generates and posts pilot episode for each of the 4 series. No paid push. Goal: 4 episodes live by EOD.

- Day 3. Episodes 5–8 (second per series). Owner verifies API access for TikTok Content Posting (apply if not granted yet).

- Day 4–5. Episodes 9–12. First analytics pulled; kill-candidates flagged early.

- Day 6–7. Episodes 13–16. First weekly report delivered Sunday 20:00 local.

## Week 2 — Optimization

- Iterate hooks based on first-week retention data. Re-edit the lowest-performing pilot with new opening 3 seconds.

- Apply for TikTok Creator Marketplace and YouTube Shorts Fund if eligible.

- Start cross-promotion: weave Easter-egg references between series for fan-discovery.

## Week 3 — First scaling decision

- Day 20 mid-month review: rank series by Composite Score (50% retention + 30% follower velocity + 20% comment rate).

- Bottom series goes on probation: 1 hook overhaul OR cancellation by Day 30.

- Top series adds 1 extra episode per week (10/week studio output).

## Week 4 — Day-30 verdict

- Kill the bottom 1–2 series unless they have a clear viral spike.

- Re-allocate freed Sora minutes to the top series + new pilot for a 5th show.

- First paid-boost test: $50 spend on the top 3 episodes of the winner.

# 6. Marketing Strategy (summary)

Full marketing playbook is in 05_Marketing_Playbook.docx. Headline points below.

## 6.1 Three growth loops, no paid spend until Day 30

- Loop 1 — Hook A/B. Every episode ships with 3 hook variants (3 different opening 3 s). The TikTok variant gets the strongest visual hook; the YouTube Shorts variant gets the strongest text hook; the Reels variant gets the strongest audio hook. Within 24 h, the winning hook becomes the canonical version.

- Loop 2 — Cliffhanger ladder. Each episode ends with a question or a cliff that forces the comment 'wait what?' or 'part 2?'. The next episode's hook directly answers — which lifts watch-time and pushes the post into the next viewer's For You feed.

- Loop 3 — Comment seed → reply video. Within the first hour we (auto) post 5–7 seed comments asking the right kind of question. We then film a 'reply' Short to the top-engaged real comment — this triggers TikTok and YouTube's 'reply to comment' boost slot.

## 6.2 Posting cadence (peak slots, US-EU overlap)

| Platform | Peak slots (local time) | Slots per series per week |
| --- | --- | --- |
| TikTok | Tue/Thu/Sat 19:00–22:00 | 3 |
| YouTube Shorts | Wed/Fri/Sun 12:00–14:00 and 20:00 | 3 |
| Instagram Reels | Mon/Wed/Fri 11:00 and 19:00 | 3 |

## 6.3 Hashtag and SEO discipline

- 3 high-volume + 4 mid-volume + 3 niche tags per platform per series.

- Episode title carries a clear pattern: SERIES NAME · EP## · 5-word hook. Pattern recognition compounds across platforms.

- YouTube descriptions get full ~150-word summaries with 8 keywords; TikTok and Reels get 1 sentence + tags.

# 7. Files in this studio

| File | Purpose | You touch it… |
| --- | --- | --- |
| 00_MASTER_PLAN.docx | This document — strategy, KPIs, roles, cadence | Re-read weekly until habits stick |
| 01_Series_Bible.docx | Premise, characters, 10-episode arcs for S1–S4 | Reference / approve direction |
| 02_Week1_Scripts_and_SoraPrompts.docx | Eight ready-to-produce episodes (Week 1) | Skim before approving production |
| 03_Sora_Prompt_System.docx | Reusable prompt templates and Sora best practices | Reference when generating manually |
| 04_Production_Budget.xlsx | Per-episode and monthly token+API costs; scaling scenarios | Update only the blue cells |
| 05_Marketing_Playbook.docx | Hooks, hashtags, posting times, growth loops, paid plays | Reference / approve paid pushes |
| 06_Automation_Pipeline.md | n8n / Make workflow blueprint with API checklist | Hand to a developer or follow yourself |
| 07_Daily_Operations.docx | Concrete checklist for each day of the week | Use daily, especially first 30 days |

After Day 30 the studio will produce a Day-30 Decision Memo in the same folder, with a kill/scale recommendation per series.

# 8. Risks and counters

| Risk | Likelihood | Impact | Counter |
| --- | --- | --- | --- |
| Sora subscription rate-limited or paused | Medium | High | Pre-render 14 days of clips in advance; fall back to Kling 1.6 or Luma Ray for overflow |
| TikTok Content Posting API not approved | Medium | Medium | Use mobile auto-uploader (e.g., Postiz, Metricool) until approved; apply Day 1 |
| Algorithm flags AI content | Low–Medium | Medium | Always voice-over with ElevenLabs (human-feeling) and add real B-roll cutaways; never label as AI in description; comply with required AI-disclosure flags |
| Series concept doesn't resonate | High by design | Low (planned) | 4-series A/B/C/D is the counter; Day-30 kill rule pre-committed |
| Burnout / over-investment in production | Medium | High | Two approval gates only; weekly production cap; no daily owner involvement |

This plan deliberately under-invests on Day 1 to keep the first month under $200 in cash cost. The biggest spend (Sora) is already a sunk subscription. The plan moves to spend only after the algorithm picks a winner.