## Cover
PROJECT LEDGER
Buy-and-build roll-up of accounting vendors & firms across PL / IT / CY, with AI overlay
Model version: v1.0 ¦ Currency: EUR (thousands) ¦ Periodicity: Annual FY26–FY30 ¦ Author: Founder (Viktar D.)
STRATEGIC THESIS
• Acquire 8–14 small accounting firms and niche bookkeeping software vendors over 5 years across PL/IT/CY
• Pay 3–6x EBITDA on entry (fragmented long-tail; aging owners; sub-€2M revenue firms)
• Integrate on common AI-powered tech stack (OCR, auto-categorization, agent-style review)
• Drive EBITDA margin from typical 10–15% to 25–35% via automation + shared services
• Exit Year 5–7 to strategic (Visma, TeamSystem, Zucchetti, Sage) or PE secondary at 8–12x EBITDA
• Multiple arbitrage spread = ~5–6x EBITDA at exit per €1 invested; targeted IRR 25–35%
SCENARIO SWITCH (cell C16): 1=Base, 2=Bull, 3=Bear | 1
TAB GUIDE
Checks | Integrity checks: BS balances, NI ties, cash ties
Inputs | All hardcoded assumptions (blue cells)
Country Mix | PL/IT/CY market sizing & acquisition funnel
M&A Schedule | Deal-by-deal pipeline with EV/EBITDA/synergy math
Operating | Bottom-up consolidated revenue and EBITDA build
IS | Income Statement
BS | Balance Sheet
CF | Cash Flow Statement (indirect method)
Debt | Acquisition financing tranches and amortization
Scenarios | Base / Bull / Bear assumption deltas
Sensitivity | Exit multiple × organic growth → IRR/MoIC
100-Day Plan | Day-by-day execution Gantt with owners & deliverables
Outputs | Headline KPIs & charts
Sources | All data sources with URLs

## Checks
INTEGRITY CHECKS
Check | FY26 | FY27 | FY28 | FY29 | FY30
BS balance: Assets − (Liab + Equity)
Cash check: CF closing cash − BS cash
NI tie: IS net income − CF NI
ALL CHECKS MUST RETURN 0. Conditional formatting: red if non-zero.

## Inputs
INPUTS & ASSUMPTIONS
Blue = hardcoded inputs. Black = computed. Source notes column E.
Section | Value | Unit | Source / Rationale
MACRO & FX
Reporting currency | EUR |  | Base currency for consolidation
Reporting unit | Thousands |  | All values in EUR '000 unless stated
FX: EUR/PLN (avg FY26) | 4.3 | PLN | NBP avg 2025-26; flat assumption
FX: EUR/EUR (avg) | 1 | EUR | Italy & Cyprus are EUR
Corp tax rate PL (CIT) | 19% | % | PL CIT 19% (9% small CIT possible)
Corp tax rate IT (IRES+IRAP) | 27.9% | % | IRES 24% + IRAP ~3.9% = ~27.9% effective
Corp tax rate CY | 12.5% | % | Cyprus headline 12.5% (Pillar 2: 15% min for large groups)
Holdco effective tax rate | 20% | % | Blended weighted by mix; CY holdco can lower further
CAPITAL & FINANCING
Seed equity raised (closed Day 1) | 250 | €k | Lean seed €50–250k; we use upper bound
Seed extension (Day 90, on traction) | 750 | €k | Bridge to Series A — angel/strategic
Series A (Month 9, acquisition capital) | 6000 | €k | PE/sponsor for first 2 deals + WC
Acquisition debt ratio (% of EV) | 40% | % | European mid-market: 35–45% senior debt typical
Acquisition debt rate (EURIBOR + 600 bps) | 8.5% | % | EURIBOR ~2.5% + 600 bps senior margin = ~8.5%
Debt tenor (years) | 5 | yrs | Bullet or amortizing — model uses 5y bullet for term loan
M&A PIPELINE & MULTIPLES
Acquisitions Year 1 (FY26) | 2 | deals | Founder + 1 FTE M&A; PL anchor + CY toehold
Acquisitions Year 2 (FY27) | 3 | deals | Add IT entry (1) + PL bolt-on (2)
Acquisitions Year 3 (FY28) | 3 | deals | Steady cadence — 1 per geo
Acquisitions Year 4 (FY29) | 3 | deals | Continued cadence; scale operations
Acquisitions Year 5 (FY30) | 3 | deals | Pre-exit; build to size
Avg target revenue (acquired co) | 800 | €k | Sub-€2M sweet spot; PL skews smaller, IT larger
Avg target EBITDA margin (pre-deal) | 12% | % | Typical mom-and-pop bookkeeping firm: 10–15%
Entry EV/EBITDA multiple (Base) | 4.5 | x | PL 3–5x; IT 5–8x; CY 3–5x; weighted ~4.5x
Exit EV/EBITDA multiple (Base, Y5) | 10 | x | European SMB SaaS at scale; Visma 2023 secondary implied ~22x on group
Transaction costs (% of EV) | 5% | % | Lawyers, accountants, advisors
Earnout deferred (% of EV) | 20% | % | Standard 20% earnout over 2–3 years
OPERATING DRIVERS
Organic revenue growth (acquired cohort) | 8% | % | 8% blended; SMB churn-adjusted
EBITDA uplift from AI/automation (per year) | 4% | ppts | OCR + auto-categorization + cross-sell; +400 bps/yr first 2 yrs
EBITDA margin cap (mature) | 30% | % | Reasonable steady-state for hybrid services+SaaS
Holdco SG&A (annual, FY26 baseline) | 480 | €k | Founder + 2 FTE + tools (3-5 head HQ + tooling)
Holdco SG&A growth rate (per year) | 20% | % | Hires for finance/legal as deals scale
Integration cost (% of target rev, one-time) | 10% | % | Tech migration + rebrand + HR
D&A (% of revenue) | 3% | % | Goodwill not amortized under IFRS; D&A from tech capex
Capex (% of revenue, organic) | 4% | % | Platform engineering + integrations
Working capital days (NWC) | 30 | days | Typical accounting services collection cycle
EXIT & VALUATION
Exit year | 5 | yr | Plan-year 5 sale; can extend to 7

## Country Mix
MARKET SIZING & ACQUISITION FUNNEL
Sources: agent research (Eurostat + national stat offices + industry associations); see Sources tab
Metric | Poland (PL) | Italy (IT) | Cyprus (CY) | Total / Notes
Number of registered accounting/bookkeeping firms | 52847 | 127000 | 800 | PL + IT = 99% of universe
Estimated annual accounting market size (€M) | 275 | 1350 | 53 | PL+IT+CY ~€1.68B addressable
Number of SMBs (<50 employees, '000) | 2400 | 4200 | 50 | Eurostat SBA factsheets
E-invoicing mandate status | KSeF Feb 2026 | SdI since 2019 | EU 2030 ViDA | Major demand driver
Avg local accountant salary (€/yr fully loaded) | 18000 | 38000 | 32000 | Glassdoor + national assoc
Local M&A multiple range (EV/EBITDA) | 4 | 6.5 | 4 | PL 3–5x; IT 5–8x; CY 3–5x — midpoint shown
Long-tail acquisition targets (revenue <€2M) | 8500 | 22000 | 250 | Estimate (~16% of universe)
Realistic 5Y acquisition target | 6 | 5 | 3 | Conservative funnel (~0.07% of long-tail)
ENTRY SEQUENCE & RATIONALE
Phase 1 — Poland (Months 0–9) | KSeF mandate creates forced-buyer dynamics; lowest multiples; 8.5k long-tail targets; entry through 1 anchor firm acquisition + 1 software vendor bolt-on
Phase 2 — Cyprus (Months 3–6) | Set up holdco for IP and tax optimization; small acquisition for tax/audit nicheservice — used as M&A/finance hub. Pillar 2 may erode advantage; still favorable for sub-€750M groups.
Phase 3 — Italy (Months 9–18) | Higher multiples but proven consolidation precedent (TeamSystem, Zucchetti). Enter via 1 commercialista acquisition with strong digital practice. Defer until we have €5M+ to deploy.

## M&A Schedule
DEAL-BY-DEAL PIPELINE
All amounts in €'000. Targets are profile sketches; replace with real LOIs as pipeline materializes.
Codename | Geo | FY | Target rev (€k) | Tgt EBITDA margin | Tgt EBITDA (€k) | Entry multiple | EV (€k) | Equity (€k) | Debt (€k) | Earnout (€k)
LEDGER-1 (PL anchor) | PL | FY26 | 1200 | 13% |  | 4
LEDGER-2 (CY hub) | CY | FY26 | 400 | 18% |  | 4
LEDGER-3 (PL software) | PL | FY27 | 900 | 20% |  | 5
LEDGER-4 (IT anchor) | IT | FY27 | 1500 | 15% |  | 6.5
LEDGER-5 (PL bolt-on) | PL | FY27 | 700 | 12% |  | 4
LEDGER-6 (IT commercialista) | IT | FY28 | 1100 | 14% |  | 6
LEDGER-7 (PL payroll niche) | PL | FY28 | 800 | 18% |  | 5
LEDGER-8 (CY audit bolt-on) | CY | FY28 | 500 | 20% |  | 4.5
LEDGER-9 (IT bolt-on) | IT | FY29 | 1300 | 15% |  | 6.5
LEDGER-10 (PL ERP niche) | PL | FY29 | 1000 | 16% |  | 5
LEDGER-11 (CY corp services) | CY | FY29 | 600 | 22% |  | 4.5
LEDGER-12 (IT scale-up) | IT | FY30 | 2000 | 18% |  | 7
LEDGER-13 (PL bolt-on) | PL | FY30 | 900 | 16% |  | 5
LEDGER-14 (PL e-invoice) | PL | FY30 | 1100 | 17% |  | 5.5
TOTAL
DEPLOYED CAPITAL BY YEAR
Year | # deals | Total EV (€k) | Equity (€k) | Debt (€k) | Earnout (€k)
FY26
FY27
FY28
FY29
FY30

## Operating
CONSOLIDATED OPERATING BUILD
Bottom-up: acquired cohort revenue (full-year basis from acquisition year) × organic growth × AI margin ramp
Line | FY26 | FY27 | FY28 | FY29 | FY30
Acquired cohort revenue (€k)
EBITDA margin: start (pre-uplift)
EBITDA margin: AI uplift (years from FY27) | 0%
EBITDA margin: total
Cohort EBITDA (€k)
Holdco SG&A (€k)
Integration costs (one-time, €k)
GROUP EBITDA (€k)
Group EBITDA margin

## IS
INCOME STATEMENT (EUR '000)
Line | FY26 | FY27 | FY28 | FY29 | FY30
Revenue
EBITDA
D&A
EBIT
Interest expense
EBT
Tax
NET INCOME
NI (for check)

## BS
BALANCE SHEET (EUR '000)
Simplified for pre-Series-A pitch; full BS to be modeled with detailed WC, PP&E rolls in v2.
Line | FY26 | FY27 | FY28 | FY29 | FY30
Cash & equivalents
Goodwill & intangibles (cum.)
Working capital (NWC)
PP&E (cumulative capex - D&A)
TOTAL ASSETS
Debt
Earnout liability
Paid-in capital
Retained earnings
TOTAL LIAB + EQUITY

## CF
CASH FLOW STATEMENT (EUR '000)
Net income
+ D&A
− Δ NWC
OP CASH FLOW
− Capex
− Acquisitions (equity portion)
INVESTING CASH FLOW
+ Debt drawings
+ Equity raised (one-time per round) |  | 0 | 0 | 0
FINANCING CASH FLOW
NET CHANGE IN CASH
Opening cash | 0
CLOSING CASH

## Debt
ACQUISITION DEBT SCHEDULE
Simplified: each year's acquisition debt assumed drawn at start of year, interest accrued at year-end.
Line | FY26 | FY27 | FY28 | FY29 | FY30
New debt drawn (€k)
Opening debt balance | 0
+ New drawings
CLOSING debt balance
Interest expense (€k)
Net debt / EBITDA

## Scenarios
SCENARIO MATRIX
Toggle scenario on Cover sheet (cell C16): 1=Base, 2=Bull, 3=Bear
Driver | Base | Bull | Bear
Entry EV/EBITDA multiple | 4.5 | 3.8 | 5.5
Exit EV/EBITDA multiple (Y5) | 10 | 13 | 7
Organic growth | 8% | 14% | 3%
EBITDA AI uplift per year | 4% | 6% | 2%
Mature EBITDA margin cap | 30% | 38% | 22%
Deal cadence (deals/yr avg) | 2.8 | 3.4 | 2
Holdco SG&A growth/yr | 20% | 15% | 25%

## Sensitivity
SENSITIVITY: EXIT MoIC
Money-on-Money (MoIC) at exit Y5: equity invested → exit equity value
Exit multiple ↓ × Organic growth → | 3% | 5% | 8% | 11% | 14%
7 | 1.3539 | 1.5193 | 1.7857 | 2.0753 | 2.3893
8.5 | 1.7971 | 1.9979 | 2.3214 | 2.673 | 3.0544
10 | 2.2403 | 2.4765 | 2.8571 | 3.2708 | 3.7194
11.5 | 2.6835 | 2.9552 | 3.3929 | 3.8686 | 4.3845
13 | 3.1267 | 3.4338 | 3.9286 | 4.4663 | 5.0495
Reading: green ≥ 3x MoIC; yellow 2–3x; red < 2x

## 100-Day Plan
100-DAY EXECUTION PLAN — FOUNDER + 2 FTE LEAN SEED
Daily owner: Founder unless stated. Mark Status as Planned / In-progress / Done. Color-code by workstream.
Day | Phase | Workstream | Action / Milestone | Owner | Deliverable | Status
1 | Foundation | Legal | Incorporate Cyprus holdco (Ltd) + open bank account | Founder + lawyer | Cert of incorp + IBAN | Planned
2 | Foundation | Legal | Draft & sign cofounder agreement, share split, vesting (4yr / 1yr cliff) | Founder + cofounder lawyer | Signed shareholders agreement | Planned
3 | Foundation | Capital | Close €250k seed (founders + 2-3 angels) | Founder | Wire receipt + SAFE/equity docs | Planned
4 | Foundation | Branding | Lock company name, trademark search in PL/IT/CY + domain & socials | Cofounder (Ops) | Trademarks filed, domains acquired | Planned
5 | Foundation | Hiring | Post job ads: M&A Associate (PL-based) + Engineer (remote) | Founder | 2 job posts live, ATS in place | Planned
7 | Foundation | Tools | Set up Notion/Linear, Slack, Google Workspace, HubSpot CRM | Cofounder | All accounts live + onboarding playbook | Planned
10 | Foundation | Investors | Build pre-Series-A target list (40 funds) + warm intros | Founder | Investor CRM with 40 targets | Planned
15 | Foundation | Branding | Launch website + LinkedIn company page + investor one-pager | Cofounder | ledger.co live + 1-pager PDF | Planned
16 | Sourcing | M&A | Build PL target longlist: 80–120 small accounting firms + niche software | M&A Associate | PL longlist v1 | Planned
18 | Sourcing | Market | Engage Polish accounting association (KIDP) — partnership talks | Founder | Meeting set with KIDP exec | Planned
20 | Sourcing | M&A | Mailer + cold-call campaign: 60 owners contacted in PL | M&A Associate | 60 owner touchpoints logged | Planned
22 | Sourcing | Tech | Build internal due-diligence template (financial + tech + customer) | Founder + auditor | DD checklist + data room template | Planned
25 | Sourcing | Capital | Engage Series-A advisor / banker; agree mandate for €5–7M raise | Founder | Signed advisor mandate | Planned
28 | Sourcing | M&A | Set up CY local advisor (accounting + corp services) | Founder | CY services agreement signed | Planned
30 | Sourcing | M&A | First 10 LOI conversations PL — qualify down to 5 active | M&A Associate | 5 active prospects | Planned
35 | Sourcing | Tech | Buy/license OCR engine (Veryfi/Klippa/Rossum) + invoice classifier; integration spec | Engineer | Vendor signed + spec drafted | Planned
40 | Sourcing | M&A | Site visit + initial DD on PL Target #1 (LEDGER-1 anchor) | Founder + M&A Assoc | DD findings memo | Planned
42 | Sourcing | M&A | Verbal LOI to PL Target #1 — €1.2M rev × 4.0x EBITDA | Founder | Term sheet drafted | Planned
45 | Sourcing | M&A | Identify CY target — small audit/tax services firm (LEDGER-2) | Founder | CY pipeline activated | Planned
46 | Closing | Legal | Sign LOI with PL Target #1 (exclusivity 60 days) | Founder + lawyer | Signed LOI + exclusivity | Planned
50 | Closing | Tech | Build MVP of AI bookkeeping assistant: invoice ingestion + auto-categorization (Polish VAT codes) | Engineer | MVP demo-able | Planned
52 | Closing | M&A | Full DD pack on PL Target #1: financial, legal, tax, IT, customer concentration | M&A Assoc + Big-4 advisor | DD report (50pp) | Planned
55 | Closing | Branding | Launch sector blog: KSeF prep guide for SMBs (lead-gen) | Cofounder (Marketing) | 3 articles live + 1000 visits | Planned
58 | Closing | M&A | Site visit CY Target — agree price range €1.6M × 4.0x = €1.6M EV | Founder | CY LOI drafted | Planned
60 | Closing | Capital | Series-A teaser deck + investor outreach started (8–10 funds) | Founder + banker | 10 fund meetings booked | Planned
62 | Closing | Legal | Negotiate SPA on PL Target #1 — earnout, reps, warranties, escrow | Lawyer | SPA v2 ready to sign | Planned
65 | Closing | M&A | Investment committee approval (founders + lead angel) for PL #1 | Founder | IC memo + decision log | Planned
68 | Closing | Closing | PL Target #1 CLOSES — funds wired, control passes | All | Closing pack archived; press release | Planned
70 | Closing | Integration | Day 1 PL #1 integration: keep brand, retain founder 2 yrs, integrate finance only | Cofounder Ops | 100-day integration plan signed | Planned
72 | Closing | Tech | Migrate PL #1 customer data into AI platform (read-only sync first) | Engineer | Data pipeline live | Planned
75 | Closing | M&A | CY Target #2 LOI signed | Founder | Signed LOI | Planned
76 | Scale | Capital | Open Series-A data room (financials, deal pipeline, AI demo, customer refs) | Founder + CFO | VDR live with 200 docs | Planned
78 | Scale | Capital | First 5 Series-A investor pitches in person (Warsaw, London, Amsterdam) | Founder | 5 pitches delivered | Planned
80 | Scale | Sales | Cross-sell pilot: offer AI bookkeeping to PL #1's 200 customers — convert 30 to AI tier | Cofounder Ops + acquired team | 30 customers on AI tier (~€60k ARR uplift) | Planned
82 | Scale | M&A | Build IT (Italy) target longlist — 80 commercialisti firms + niche vendors | M&A Assoc | IT longlist v1 | Planned
85 | Scale | Hiring | Hire Country Manager Poland (ex-accounting firm owner, network) | Founder | Country Mgr signed, starts Day 100 | Planned
88 | Scale | Tech | AI platform: roll out invoice auto-approval (95%+ accuracy threshold) | Engineer | Auto-approval rate metric on dashboard | Planned
90 | Scale | Capital | Term sheets received from 2-3 Series-A funds; negotiate | Founder + banker | Term sheet selected | Planned
92 | Scale | M&A | CY Target #2 closes — small audit firm (~€400k rev) | Founder | 2 acquisitions completed in 92 days | Planned
95 | Scale | Branding | Industry conference talk in Warsaw — position as 'roll-up + AI' thesis | Founder | Talk delivered + 100 leads | Planned
97 | Scale | Capital | Sign Series-A term sheet (€5–7M @ valuation €15–25M post) | Founder | Signed TS | Planned
98 | Scale | M&A | Begin IT Target #1 outreach (commercialista with digital practice) | Founder + IT advisor | 10 IT targets contacted | Planned
99 | Scale | Ops | 100-day review: KPI dashboard, lessons learned, Q2 plan | Founder | Q2 plan signed off | Planned
100 | Scale | Comms | Founder LP / angel update: 2 deals closed, Series A signed, IT pipeline open | Founder | Update email + Loom video | Planned

## Outputs
KPI DASHBOARD
KPI | FY26 | FY27 | FY28 | FY29 | FY30
Revenue (€k)
EBITDA (€k)
EBITDA margin
Net income (€k)
# deals YTD (cumulative)
Cumulative invested (€k)
Closing cash (€k)
Net debt / EBITDA
EXIT VALUATION — YEAR 5 (Base case)
FY30 EBITDA (€k)
Exit EV/EBITDA multiple
Enterprise Value at exit (€k)
− Net debt (€k)
Equity value at exit (€k)
Total equity invested (€k)
MoIC (Money-on-Money)
IRR (approx, 5-yr)

## Sources
DATA SOURCES & REFERENCES
Category | Source
Visma history & PE | https://hgcapital.com/portfolio/visma
Visma 2023 €19B secondary | https://www.visma.com/news/visma-attracts-new-investors-for-further-international-expansion-in-a-transaction-valuing-the-company-at-eur-19-billion
Visma 2020 Warburg/TPG | https://warburgpincus.com/2020/08/24/new-investment-in-visma-valued-at-us12-2-billion-in-the-worlds-largest-ever-software-buyout
Visma annual report 2024 | https://www.visma.com/annualreport/2024
Visma M&A playbook podcast | https://www.mascience.com/podcast/how-to-build-a-global-m-a-machine-with-local-expertise
Visma Fiscozen (Italy 2024) | Internal: Visma news release — Italian tax advisory acquisition
Visma Holded (Spain 2021) | Visma's Spanish AI accounting platform — relevant comparable
Constellation Software | https://www.csisoftware.com/operating-groups
Topicus.com spin-out | https://topicus.com/news/constellation-software-inc-completes-spin-out-of-topicuscom-inc
Software valuation multiples | https://aventis-advisors.com/software-valuation-multiples
Constellation comp analysis | https://rollupeurope.com/p/utm-source-rss-utm-medium-rss-utm-campaign-boss-your-comps-pt-3-do-software-rollups-deserve-constell
Kabilio (Spain AI accounting) | https://pulse2.com/kabilio-e4-million-raised-to-expand-ai-platform-for-accounting-firms-in-spain
VC accounting roll-ups trend | https://www.transacted.io/venture-firms-target-accounting-roll-ups-with-ai-automation-play
PL: KSeF mandate | Polish Ministry of Finance — KSeF obligatory implementation Feb 2026
IT: SdI fattura elettronica | Agenzia delle Entrate — SdI mandatory since 2019 for B2B
CY: IFRS adoption | Cyprus Companies Law CAP 113 — IFRS required all entities
EU ViDA package | European Commission — VAT in Digital Age proposal
Spanish AI accounting category | Holded, Anfix, Quipu, Contasimple, Xolo — references